THE CRITICAL PATH METHOD OF PROJECT MANAGEMENT -Anon

Introduction

Since it was first designed in 1957, the critical path method has become an important way that business owners or project managers can oversee large undertakings. It encourages efficiency by dividing complicated efforts into a series of small tasks with costs and resources associated with each, and its development allows managers to see where potential breakdowns might occur and what resources are available to deal with them if that happens.

## Basics

The benefit of using the critical path method for the project manager is that it’s an effective way to see which delays can be handled with built-in slack time -- the “float” -- and which will cause a project to fall behind schedule. Since there is no float on the critical path by definition, if a deadline is set in stone it means that the manager has to take steps to get everything back on schedule. In some cases, activities can be pruned or performed in parallel, which is known as “fast tracking,” and in some cases, added resources shrink the amount of time needed to complete tasks along the way, known as “crashing.”

Origins

The critical path method was developed at the DuPont Company in 1957 by a pair of mathematicians who were looking at ways to avoid the costs of plant shutdowns and restarts caused by inefficient scheduling. Their research showed that money could be saved by focusing efforts on performing the right tasks at the right times, rather than flooding the problem with labor to stay on schedule. This saved DuPont 25 percent on shutdowns, and James Kelley and Morgan Walker published the first paper on their findings in 1959. Ironically, DuPont then dropped the CPM system when the management team responsible for it changed.

Adoption

Although CPM at DuPont was fading, Mauchly Associates picked it up. Beginning in 1959, the company helped commercialize CPM by focusing on scheduling efficiencies rather than cost savings, organizing CPM training and transforming it into a new way of doing business for construction companies. Catalytic Construction bought into the concept in 1961, and several others quickly followed. Because of the primitive nature of computer systems at that time, the cost of the process was a barrier to entry.

Evolution

In addition to its ability to reduce the complexity of larger projects by breaking them into component tasks, the critical path method became popular because of the innovations in computer hardware and software. In the first few decades of the critical path method, the tools were bulky mainframe computers used by specialists who often required months of training. The PC revolution brought scheduling management software to the desktop, and the rise of computer networking allowed the results to be shared easily among team members.

Associated Concepts

Several other program management tools have been developed to increase the effectiveness of the critical path method. The Program Evolution and Review Technique, or PERT, developed by the U.S. Navy around the same time that the DuPont mathematicians were hard at work, has a similar purpose in estimating the time it takes to complete specific tasks, but PERT is based on probability rather than offering an absolute time. Coming out of the same project, the Work Breakdown Structure dividing a project into deliverables and tasks was instituted by the Department of Defense in 1962. In 1984, the Theory of Constraints, which introduces the concept of constraints and the need to restructure an organization around them, was introduced by Eliyahu M. Goldratt and later expanded into critical chain program management.

## Definition

Critical path is a term that has its origin in project management. It requires the manager to list the required tasks needed to complete a particular project, the time each will likely take and the dependencies between the activities. These tasks are usually laid out in a diagram, with the project manager tracing the path from the first task to the last and noting the earliest that each task along that path can start and the latest it can be completed without causing a delay. That’s the best outcome for how quickly your project can be completed. It’s called the critical path, because it has no slack; every task on the path is critical, and a delay in any task causes a project delay.

Slack

Slack, or float, refers to the amount of days or hours that various related tasks can be delayed without pushing the project back. The critical path, by definition, has no slack. But other tasks not on the critical path may have built-in float. For example, if it’s a Wednesday and you’re opening your restaurant on Friday, but your dairy products haven’t been delivered, it’s not a big deal if there's only one day between order and delivery; you have a day of slack built in. On the other hand, if your training program for servers takes four days and you’re scheduled to open in two, that means you can’t open on time -- unless you change the path.

Schedule Compression

Schedule compression, or pruning, can occur when a manager decides that the slack can be eliminated by cutting some of the critical tasks out or completing them in less time. Maybe you decide that you can cut the training to two days by racing through certain sections or leaving out points you consider obvious or eliminating topics you think your employees already understand. That gets your project back on schedule -- but perhaps at a cost if the rushed-through training leaves servers unprepared.

Performing in Parallel

A critical path can also recover from unanticipated slack if tasks once scheduled to be performed in a series can instead be performed in parallel -- at the same time. That can reduce the critical path, but it usually increases the risks as well. You might have originally scheduled the training to take place after your restaurant was built, but instead you choose to conduct the events in parallel. That might work to save time, but it may cause both events to take longer than planned or consume more resources because of decreased production and efficiency. It might be harder to conduct training with the noise of construction and harder to do the construction while manoeuvring around a class.

Crashing

Another way of overcoming slack on the critical path is crashing, or throwing more resources at a task to get it completed faster. In the restaurant example, that might mean hiring additional staff and make the training more specialized, so everyone doesn’t need to be trained in everything. Or it may mean hiring more trainers to provide individual attention to get the staff up to speed faster. In any case, it get your path back on schedule but at a big cost to your budget.